## Event Planning
Event: | Annual Company Gala
Date: | 2026-09-15
Budget: | 25000
Task | Category | Owner | Due | Budget | Actual | Done?
Book venue | Venue | Events Manager | 2026-07-15 | 5000 | 4800 | Yes
Hire catering | Food | Events Manager | 2026-07-20 | 8000 | 0 | No
Send invitations | Communications | EA | 2026-08-01 | 500 | 480 | Yes
Book AV equipment | Tech | IT | 2026-08-10 | 1500 | 0 | No
Arrange transport | Logistics | Admin | 2026-08-15 | 1200 | 0 | No
Order decorations | Décor | Events Manager | 2026-08-20 | 1000 | 0 | No
Hire photographer | Media | Events Manager | 2026-08-01 | 2000 | 1800 | Yes
Print programs | Printing | Admin | 2026-09-01 | 300 | 0 | No
Confirm guest list | Admin | EA | 2026-09-05 | 0 | 0 | No
Final run-through | Planning | All | 2026-09-14 | 0 | 0 | No
TOTAL