## Launch Checklist
Phase | Task | Owner | Due Date | Done? | Priority
Research | Define target persona | Product | 2026-07-10 | Yes | High
Research | Competitive analysis | Marketing | 2026-07-12 | Yes | High
Research | Pricing strategy | Finance | 2026-07-15 | Yes | High
Build | MVP features locked | Product | 2026-07-20 | Yes | High
Build | QA testing complete | QA | 2026-07-28 | No | High
Build | Beta user feedback | Product | 2026-08-01 | No | Medium
Marketing | Landing page live | Design | 2026-08-01 | No | High
Marketing | Email campaign | Marketing | 2026-08-05 | No | Medium
Marketing | Social media plan | Marketing | 2026-08-05 | No | Medium
Launch | Support docs ready | Support | 2026-08-08 | No | High
Launch | Monitoring set up | DevOps | 2026-08-09 | No | High
Launch | Go live | All | 2026-08-10 | No | Critical
Post-Launch | Collect feedback | Product | 2026-08-17 | No | Medium
Post-Launch | Retrospective | All | 2026-08-20 | No | Low