## Project Tracker
Free from excelback.com - more free Excel templates & tools
Simple Project Tracker
Task | Owner | Start date | Due date | Status | % complete | Notes
Define project scope | Alex | 2026-01-06 | 2026-01-10 | Done | 100%
Gather requirements | Priya | 2026-01-08 | 2026-01-15 | Done | 100%
Build wireframes | Jordan | 2026-01-13 | 2026-01-22 | In progress | 60%
Develop backend | Sam | 2026-01-20 | 2026-02-10 | In progress | 35%
Develop frontend | Jordan | 2026-01-22 | 2026-02-12 | In progress | 30%
QA testing | Priya | 2026-02-10 | 2026-02-20 | Not started | 0%
Client review | Alex | 2026-02-20 | 2026-02-24 | Not started | 0%
Launch | Sam | 2026-02-25 | 2026-02-27 | Not started | 0%